## Sheet1
Bug Status report
Prepared by: Jernej Uranič
Project: New functionality on Website
Date of preparation: DD/MM/YYYY

Issues:
Issues reported: 22
Issues resolved: 20
Issues opened;2
Open issue ID: project-1234, project-1235
The two issues still opened are the result of graphic elements were not ready
What was tested:
- Complete UI/UX
- Contact form
- Images
- Urls
Bugs found:
- Contactform submit button was not functional
- Dead anchor link on DATA VAULT site
- Name field missing from contact form email

Pending deliverables:
Project: Website Testing
Scheduled date: DD/MM/YYYY
Reason for extending: Graphic elements were not ready

No. of test planned: 56
No. of test executed: 48
Test cases passed:40
Test cases failed:8

Type of testing performed: smoke testing